## Dashboard
National Epoxy Pros Finish Mode - Archive + Sandbox Command Workbook
Current Mission | Finish National Epoxy Pros first. Everything else waits. | Readiness Area | Score | Weight | Weighted | Status
Current Score | 85 | Source Truth | 100 | 15% | 1500% | Locked
Target Preview Score | 90 | Drive / Assets | 95 | 15% | 1425% | Strong
Target Production Score | 95 | Vercel Config | 60 | 10% | 600% | Partial
Active Branch | launch/nep-emergency-site | App Scaffold | 15 | 30% | 450% | Missing
Primary Repo | Strategic-Minds/NEP | Preview Validation | 0 | 30% | 0% | Missing
Drive Root ID | 1OpS0QiP7xJVzyfku_Ji6i9ZtzrR63iIL
Vercel Team | Strategic Minds Advisory | Decision | Status
Supabase Project | Strategic Minds Advisory / ACTIVE_HEALTHY | Archive folder | Manual create required or retry when Drive write gate opens
Protected Gate | No production deploy, DNS, secrets, payments, live messages, or destructive DB without explicit Jeremy approval. | Sandbox lane | Approved for preview/sandbox only
|  | Env sync | Approved by Jeremy for strategy; do not expose secret values
|  | Next P0 | Create health route, validator route, receipts route, .env.example
Formula Check
Weighted System Score | 39.75
Gap to Preview | 5
Gap to Production | 10

## Archive Plan
NEP Archive Lane Plan
Folder | Purpose | Owner | Access Rule | Create Status | Priority | Notes
NEP Archive 20260705 | Project-level vault for clean base snapshots and proof | Jeremy | Restricted / Jeremy approval only | Pending manual create | P0 | Create under NEP Drive root
01 Clean Base Snapshots | Freeze known-good state for reuse | Jeremy | Viewer for agents unless approved | Pending | P0 | No unstable files
02 Receipts | Store validation and action receipts | Jeremy | Viewer for agents unless approved | Pending | P0 | Every meaningful action leaves receipt
03 Rollback | Rollback plans and release backout proof | Jeremy | Viewer for agents unless approved | Pending | P0 | Required before production
04 Clone References | Future 5-clone / infinite-clone base references | Jeremy | Viewer for agents unless approved | Pending | P1 | Do not clone client-specific truth blindly
05 Approved Env Map | Env variable names and ownership, no secret values | Jeremy | Restricted | Pending | P0 | Never paste secrets in docs
06 Jeremy Approval Only | Manual approvals and gates | Jeremy | Restricted | Pending | P0 | Production and credential approvals live here

## Sandbox Execution
Vercel Sandbox + Agent Execution Plan
Step | Action | Tool/Lane | Allowed? | Approval Needed | Expected Output | Status | Risk
1 | Confirm GitHub launch branch | GitHub | Yes | No | launch/nep-emergency-site verified | Ready | Low
2 | Create health route | GitHub | Yes | No | app/api/health/route.ts | Next | Low
3 | Create cron validator route | GitHub + Vercel Cron | Yes | No | app/api/cron/nep-validator/route.ts | Next | Low
4 | Create receipts route | GitHub | Yes | No | app/api/receipts/route.ts | Next | Medium
5 | Create .env.example | GitHub | Yes | No | Variable names only | Next | Low
6 | Sync env values from shared Vercel/AUTO BUILDER source | Vercel | Conditional | Jeremy approval | Env attached to sandbox only | Approved strategy | High
7 | Create or attach sandbox project | Vercel Sandbox | Conditional | Jeremy approval | Sandbox preview URL | Pending | Medium
8 | Run sandbox build | Vercel | Yes after sandbox | No production approval | Build logs | Pending | Medium
9 | Repair build defects | Vercel Agent / GitHub | Yes | No | Patched branch | Pending | Medium
10 | Promote to production | Vercel | No | Explicit Jeremy approval | Production deploy | Blocked | High

## Env Approval Map
Environment Approval Map - Names Only, No Secret Values
Variable Name | Purpose | Source | Sandbox Needed | Production Needed | Secret? | Rule
NEXT_PUBLIC_SUPABASE_URL | Client Supabase URL | Shared / Supabase | Yes | Yes | No | Can be referenced by name
NEXT_PUBLIC_SUPABASE_ANON_KEY | Client Supabase anon key | Shared / Supabase | Yes | Yes | Yes | Do not print value
SUPABASE_SERVICE_ROLE_KEY | Server-side admin operations | Supabase | No unless needed | Conditional | Yes | Never expose client-side
VERCEL_TEAM_ID | Team scoping | Vercel | Yes | Yes | No | Use team ID reference only
AI_GATEWAY_API_KEY | AI Gateway | Vercel / AI Gateway | Conditional | Conditional | Yes | Sandbox only if route needs it
OPENAI_API_KEY | Fallback AI provider | Shared | Conditional | Conditional | Yes | Do not hardcode
GROQ_API_KEY | Primary/fast AI provider | Shared | Conditional | Conditional | Yes | Do not hardcode
TWILIO_ACCOUNT_SID | Messaging provider | Twilio | No | Conditional | Yes | Do not activate live messaging yet
TWILIO_AUTH_TOKEN | Messaging credential | Twilio | No | Conditional | Yes | Do not expose
CRON_SECRET | Protect cron validator | Generated | Yes | Yes | Yes | Generate/store in Vercel only

## Protected Actions
Jeremy Approval Gates
Action | Allowed Now? | Who Approves | Approval Phrase Needed | Receipt Required | Notes
Production deploy | No | Jeremy | Approve production deploy | Yes | Only after preview pass
DNS/domain change | No | Jeremy | Approve DNS change | Yes | Never during sandbox
Secret/env value mutation | Conditional | Jeremy | Approve env sync | Yes | Names may be documented; values not exposed
Payment activation | No | Jeremy | Approve payments | Yes | Not needed for preview
Live SMS/WhatsApp/email | No | Jeremy | Approve live messaging | Yes | Use safe/test mode only
Destructive DB migration | No | Jeremy | Approve destructive DB action | Yes | Prefer draft migrations
Sandbox build | Yes | Jeremy already approved sandbox lane | Sandbox lane approved | Yes | No production promotion

## Clone Readiness
Clone Readiness Audit Prep
Element | Category | Reusable? | Tokenize? | Do Not Clone Risk | Action | Owner | Status
App shell | Structure | Yes | No | Low | Promote to base after preview | Builder | Pending app scaffold
Brand colors | Brand | No | Yes | Medium | Variable tokens | Jeremy | Locked for NEP
Logo | Asset | No | Yes | High | Replace per clone | Jeremy | Locked for NEP
Contact info | Business truth | No | Yes | High | Replace per clone | Jeremy | Locked for NEP
Digital Bid form | Workflow | Yes | Minor | Low | Promote to base | Builder | Pending implementation
Visualizer rule | Integration | Conditional | Yes | Medium | Tokenize external URL | Builder | XPS rule locked
Supabase schema | Backend | Yes | Yes | Medium | Use migrations and RLS template | Builder | Pending
Env map | Operations | Yes | Yes | High | Names only, no values | Jeremy | Pending
Validation receipts | Governance | Yes | Minor | Low | Promote to base | Builder | Partial

## Receipt Log
Action Receipt Log
Timestamp | Phase | Action | Tool | Status | Verified | Blocker | Next Action | Approval Required
2026-07-05 09:03 UTC | Archive/Sandbox Prep | Created workbook artifact | artifact_tool | Complete | Workbook generated | Drive write blocked in chat | Create route files | No
2026-07-05 09:03 UTC | MCP Test | MCP health verified | AUTO BUILDER MCP | Complete | status ok | Execute write gate still blocked | Use repo-side implementation | No
2026-07-05 09:03 UTC | Vercel Config | vercel.json confirmed | GitHub | Complete | Cron config exists | Cron route missing | Create app/api/cron/nep-validator/route.ts | No

## Manual Drive Steps
Manual Drive Archive Instructions
Step | Instruction | Exact Name | Parent | Access | Done?
1 | Create project archive folder | NEP Archive 20260705 | NEP Drive root | Restricted | No
2 | Create child folder | 01 Clean Base Snapshots | NEP Archive 20260705 | Jeremy edit only | No
3 | Create child folder | 02 Receipts | NEP Archive 20260705 | Jeremy edit only | No
4 | Create child folder | 03 Rollback | NEP Archive 20260705 | Jeremy edit only | No
5 | Create child folder | 04 Clone References | NEP Archive 20260705 | Jeremy edit only | No
6 | Create child folder | 05 Approved Env Map | NEP Archive 20260705 | Restricted | No
7 | Create child folder | 06 Jeremy Approval Only | NEP Archive 20260705 | Restricted | No

## Next P0
Next P0 Implementation Queue
Priority | File | Purpose | Status | Blocks | Risk | Validation | Notes
P0 | app/api/health/route.ts | Basic system health endpoint | Not created | Vercel health check | Low | GET returns ok | First implementation file
P0 | app/api/cron/nep-validator/route.ts | 5-min validator target | Not created | Cron config | Low | GET returns validation JSON | Must be idempotent
P0 | app/api/receipts/route.ts | Receipt intake or receipt status | Not created | Validation receipts | Medium | GET/POST safe mode | No secret values
P0 | .env.example | Env variable names only | Not created | Sandbox env sync | Low | No actual values | Names only
P0 | app/api/leads/route.ts | Lead capture endpoint | Not created | Digital Bid | Medium | Safe insert or mock mode | No live messaging
P1 | app/page.tsx | Homepage | Not created | Preview | Medium | Loads brand/CTA | After API backbone